## Game Content
GAME CONTENT
Character | Left & Right Movement | Jump Movement | Interaction with Special Tiles | Interaction with Objective Tile | Idle Animation | Movement Animation
Enemy - Slime | Idle Animation | Movement Animation | Death Animation
Enemy - Flying Bat | Idle Animation | Flying Animation | Death Animation
Enemy - Jumping Squirrel | Idle Animation | Movement Animation | Jump Animation | Death Animation
UI | Gameplay HUD | Main Menu | Level Navigation UI | Pause Menu UI
Tiles | Collapsible Tile | Non-Collapsible Tile | Special Tile | Objective Tile
Sounds | Jump Sound | Death Sound
Systems | Autosave | Tile collapsing system | Graphics: Font | Helper functions: Texture rendering with Alpha Engine

## Content - Art
CHARACTERS
| Art | Animation
| Sprites | Idle | Movement | Death
Jumperman | Yes | Yes | Yes | Yes
Enemy - Slime | Yes | Yes | Yes | Yes
Enemy - Bat | Yes | Yes | Yes | Yes
Enemy - Squirrel | Yes | Yes | Yes | Yes
LEVELS
| Art | Animation
| Sprites | Collapse | Interactible
Tiles : Grass Tile (Collapsible) | Yes | Yes | No
Tiles : Special Tile (Interactible) | Yes | Yes | Yes
Tiles : Gravel Tile | Yes | No | No
Tiles : Goal Tile | Yes | No | No

## Content - Code
CODE
EPIC | Task | Notes
Character | Movement
| Interaction with Special Tile | Ability to Interact with a certain tile
Enemy | Enemy Movement Slime | Moves along a straight line of tiles
| Enemy Movement Bat | Moves in a 'V' shape, floating
| Enemy Movement Squirrel | Moves along a line of tiles, Jumps at fixed intervals
| Collision with Player + Death | Enemies die when player lands on top of them
UI | Main Menu | Mouse Navigated and Leads to Level Select, Leaderboard, Exit
| HUD | Time Elapsed, Lives Remaining, Current Level
| Pause Menu | Mouse Navigated and Leads to Main Menu, Level Select, Resume
| Level Selection Menu | Player will be able to select from unlocked levels only
Level | Tiles : Collapsible | Tiles will collapse after a short delay when player kills an enemy on it
| Tiles : Non-Collapsible | Tiles will not collapse
| Tiles : Special | Same as Collapsible, but will include the ability to be interacted with for manual collapse
| Tiles : Goal | Objective to reach for the player to beat a level
Systems | Autosave System | Game will autosave upon player clearing a level or dying in a level, retaining high score and clear status
Tile collapsing system
Graphics: Font
Helper functions: Texture rendering with Alpha Engine
Collision detection: player and goal tile
Collision detection: enemy and player
Leaderboard system
Pause feature
Tile shake before collapsing
Sounds | Audio Integration using FMod

## Backlog
BACKLOG
Completion | Priority | EPIC | Task | Owner | Type | Estimation (h) | Planned Week
Not Started | 0 - Must Have | Character | Animation : Jumperman Movement | Wee Boon | Animation | 4 | 7
Not Started | 0 - Must Have | Character | Animation : Slime Movement | Wee Boon | Animation | 4 | 7
Not Started | 0 - Must Have | Character | Animation : Bat Movement | Wee Boon | Animation | 4 | 7
Not Started | 0 - Must Have | Character | Animation : Squirrel Movement | Wee Boon | Animation | 4 | 8
Not Started | 0 - Must Have | Character | Animation : Jumperman Death | Wee Boon | Animation | 4 | 8
Not Started | 0 - Must Have | Character | Animation : Enemy Death | Wee Boon | Animation | 4 | 8
Done | 0 - Must Have | Character | Player movement | Bryan | Code | 1 | 2
Not Started | 0 - Must Have | Sounds | Audio Integration using FMod | Bryan | Code | 10 | 7
Done | 0 - Must Have | System | Tile collapsing system | Bryan | Code | 6 | 2
Done | 0 - Must Have | System | Graphics: Font | Bryan | Code | 2 | 3
In Progress | 0 - Must Have | System | Helper functions: Texture rendering with Alpha Engine | Bryan | Code | 8 | 2
Done | 0 - Must Have | System | Collision detection: player and goal tile | Bryan | Code | 1 | 3
In Progress | 0 - Must Have | System | Collision detection: enemy and player | Bryan | Code | 6 | 6
Not Started | 1 - Should Have | System | Leaderboard system | Bryan | Code | 6 | 10
Done | 1 - Should Have | System | Pause feature | Bryan | Code | 2 | 3
Not Started | 2 - Could Have | System | Tile shake before collapsing | Bryan | Code | 6 | 7
Done | 0 - Must Have | Character | 2D Sprite : Jumperman | Wee Boon | 2D Art | 4 | 2
Done | 0 - Must Have | Character | 2D Sprite : Slime | Wee Boon | 2D Art | 4 | 2
Done | 0 - Must Have | Character | 2D Sprite : Bat | Min Yi | 2D Art | 4 | 5
Done | 0 - Must Have | Character | 2D Sprite : Squirrel | Min Yi | 2D Art | 4 | 5
Not Started | 0 - Must Have | Character | Interaction with special tile | Bryan | Code | 4 | 6
In Progress | 0 - Must Have | Enemy | Enemy Movement for Slime | Dallas | Code | 6 | 8
Not Started | 0 - Must Have | Enemy | Enemy Movement for Bat | Bryan | Code | 4 | 9
Not Started | 0 - Must Have | Enemy | Enemy Movement for Squirrel | Dallas | Code | 6 | 8
Done | 0 - Must Have | Enemy | Collision with Player + Death | Bryan | Code | 4 | 2
Not Started | 1 - Should Have | Sounds | Enemy Death Sound | Dallas | Other | 2 | 10
Not Started | 1 - Should Have | Sounds | Jumperman Death Sound | Dallas | Other | 2 | 10
Not Started | 1 - Should Have | Sounds | Jump Sound | Dallas | Other | 2 | 10
Not Started | 2 - Could Have | Sounds | Tile Collapse Sound | Dallas | Other | 2 | 10
Done | 0 - Must Have | Level | Tiles : Collapsible | Bryan | Code | 1 | 4
Done | 0 - Must Have | Level | Tiles : Non-Collapsible | Bryan | Code | 1 | 4
Done | 0 - Must Have | Level | Tiles : Special | Bryan | Code | 1 | 5
Done | 0 - Must Have | Level | Tiles : Goal | Bryan | Code | 1 | 4
Done | 0 - Must Have | Level | Art : Grass Tile (Collapsible) | Wee Boon | 2D Art | 4 | 2
Done | 0 - Must Have | Level | Art : Special Tile (Interactible) | Min Yi | 2D Art | 2 | 4
Done | 0 - Must Have | Level | Art : Gravel Tile | Dallas | 2D Art | 2 | 4
Done | 0 - Must Have | Level | Art : Goal Tile | Dallas | 2D Art | 2 | 2
In Progress | 0 - Must Have | UI | Main Menu : Mouse Navigated (Level Select, Leaderboard, Exit) | Dallas | Code | 4 | 6
In Progress | 0 - Must Have | UI | HUD (Time Elapsed, Lives Remaining, Current Level) | Bryan | Code | 2 | 5
In Progress | 0 - Must Have | UI | Pause Menu : (Return to Main Menu, Level Select, Resume) | Dallas | Code | 4 | 9
Not Started | 1 - Should Have | UI | Buttons | Bryan | Code | 8 | 7
In Progress | 0 - Must Have | UI | Visuals : FONT + Art style definition | Wee Boon | Other | 4 | 6
In Progress | 0 - Must Have | UI | Visuals : Main Menu | Dallas | Other | 4 | 7
In Progress | 0 - Must Have | UI | Visuals : HUD | Dallas | Other | 4 | 7
In Progress | 0 - Must Have | UI | Visuals : Pause Menu | Dallas | Other | 4 | 7
In Progress | 0 - Must Have | UI | Visuals : Death Screen | Dallas | Other | 4 | 8
In Progress | 0 - Must Have | UI | Menu : Level Selection | Dallas | Code | 6 | 9
In Progress | 0 - Must Have | UI | Visuals : Level Selection | Dallas | Other | 4 | 10
Not Started | 1 - Should Have | System | Autosave System | Bryan | Code | 6 | 8
In Progress | 0 - Must Have | Level | Tutorial Level | Wee Boon | Level Design | 6 | 7
Not Started | 0 - Must Have | Level | Level 1 | Wee Boon | Level Design | 6 | 7
Not Started | 1 - Should Have | Level | Level 2 | Min Yi | Level Design | 6 | 8
Not Started | 1 - Should Have | Level | Level 3 | Min Yi | Level Design | 6 | 8
Not Started | 2 - Could Have | Level | Level 4 | Min Yi | Level Design | 6 | 9
Not Started | 2 - Could Have | Level | Level 5 | Min Yi | Level Design | 6 | 9
Not Started | 2 - Could Have | Level | Level 6 | Min Yi | Level Design | 6 | 10
Not Started | 2 - Could Have | Level | Level 7 | Min Yi | Level Design | 6 | 10
Not Started | 2 - Could Have | Level | Level 8 | Min Yi | Level Design | 6 | 11
Not Started | 2 - Could Have | Level | Level 9 | Min Yi | Level Design | 6 | 11
Not Started | 2 - Could Have | Level | Level 10 | Min Yi | Level Design | 6 | 11

## Project Stats
TOTAL WORKLOAD
Sum of Estimation (h)
Members | Done | In Progress | Not Started | Total per Member
Dallas | 4 | 40 | 14 | 58
Wee Boon | 12 | 10 | 30 | 52
Bryan | 20 | 16 | 44 | 80
Min Yi | 10 | 0 | 54 | 64
Grand Total | 46 | 66 | 142 | 254
AVAILABLE TIME
Length of project |  | 7 | Weeks Remaining
Average Availability : |  | 14 | Hours / Week
Size of Team |  | 4 | Members
|  | 392 | Total Available Hours
PROJECT STATS
Total Required Time VS Available Time : |  |  | 53.06%
Total Completion Rate: |  |  | 18.11%

## Gantt Chart
|  | Team Name: | Only4 |  |  | Project Start: | 2021-01-18
|  | Game Name: | Jumperman |  |  | Producer: | Dallas Lau Cheong Kin
[8 empty] | Wk 2 | [6 empty] | Wk 3 | [6 empty] | Wk 4 | [6 empty] | Wk 5 | [6 empty] | Wk 6 | [6 empty] | Wk 7 | [6 empty] | Wk 8 | [6 empty] | Wk 9 | [6 empty] | Wk 10 | [6 empty] | Wk 11 | [6 empty] | Wk 12 | [6 empty] | Wk 13
[8 empty] | Jan 18, 2021 | [6 empty] | Jan 25, 2021 | [6 empty] | Feb 1, 2021 | [6 empty] | Feb 8, 2021 | [6 empty] | Feb 15, 2021 | [6 empty] | Feb 22, 2021 | [6 empty] | Mar 1, 2021 | [6 empty] | Mar 8, 2021 | [6 empty] | Mar 15, 2021 | [6 empty] | Mar 22, 2021 | [6 empty] | Mar 29, 2021 | [6 empty] | Apr 5, 2021
[8 empty] | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Task | Epic | Assigned to | Priority | Progress | Estimated Time(h) | Start Date | End Date | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Pitch
Presentation for slides for Week 3 | Pitch | Min Yi | 0 - Must Have | 100% | 2 | 2021-01-18 | 2021-01-24 | bar: Jan 18, 2021 18 to Jan 18, 2021 24
Create Demo of game mechanics | Pitch | Bryan | 0 - Must Have | 100% | 4 | 2021-01-18 | 2021-01-24 | bar: Jan 18, 2021 18 to Jan 18, 2021 24
Game Concepts
Study Inspiration Game: Block Study | Concept | Dallas | 0 - Must Have | 100% | 2 | 2021-01-18 | 2021-01-18 | bar: Jan 18, 2021 18
Lay out concept for needed tiles | Concept | Dallas | 0 - Must Have | 100% | 4 | 2021-01-22 | 2021-01-22 | bar: Jan 18, 2021 22
Lay out enemy types to be included | Concept | Wee Boon | 0 - Must Have | 100% | 4 | 2021-01-23 | 2021-01-23 | bar: Jan 18, 2021 23
Finalize game premise and objectives | Concept | Min Yi | 0 - Must Have | 100% | 4 | 2021-01-24 | 2021-01-24 | bar: Jan 18, 2021 24
Characters
Jumperman: Character Movement | Character | Bryan | 0 - Must Have | 100% | 4 | 2021-01-18 | 2021-01-24 | bar: Jan 18, 2021 18 to Jan 18, 2021 24
Interaction with special tile | Systems | Bryan | 0 - Must Have | 0% | 4 | 2021-02-08 | 2021-02-14 | bar: Feb 8, 2021 8 to Feb 8, 2021 14
Enemy Slime : Movement | Character | Dallas | 0 - Must Have | 100% | 6 | 2021-01-18 | 2021-01-24 | bar: Jan 18, 2021 18 to Jan 18, 2021 24
Enemy Bat : Movement | Character | Bryan | 0 - Must Have | 0% | 4 | 2021-03-08 | 2021-03-14 | bar: Mar 8, 2021 8 to Mar 8, 2021 14
Enemy Squirrel : Movement | Character | Dallas | 0 - Must Have | 0% | 6 | 2021-03-01 | 2021-03-05 | bar: Mar 1, 2021 1 to Mar 1, 2021 7
Documentation
SRS | Document | Wee Boon | 0 - Must Have | 100% | 12 | 2021-01-25 | 2021-02-07 | bar: Jan 25, 2021 25 to Feb 1, 2021 7
TDD | Document | Bryan | 0 - Must Have | 100% | 12 | 2021-02-08 | 2021-02-14 | bar: Feb 8, 2021 8 to Feb 8, 2021 14
PPD | Document | Dallas | 0 - Must Have | 100% | 12 | 2021-02-08 | 2021-02-14 | bar: Feb 8, 2021 8 to Feb 8, 2021 14
Art and Animation
Animation : Jumperman Movement | Animation | Wee Boon | 0 - Must Have | 0% | 4 | 2021-02-22 | 2021-02-23 | bar: Feb 22, 2021 22 to Feb 22, 2021 23
Animation : Slime Movement | Animation | Wee Boon | 0 - Must Have | 0% | 4 | 2021-02-24 | 2021-02-25 | bar: Feb 22, 2021 24 to Feb 22, 2021 25
Animation : Bat Movement | Animation | Wee Boon | 0 - Must Have | 0% | 4 | 2021-02-26 | 2021-02-27 | bar: Feb 22, 2021 26 to Feb 22, 2021 28
Animation : Squirrel Movement | Animation | Wee Boon | 0 - Must Have | 0% | 4 | 2021-03-01 | 2021-03-02 | bar: Mar 1, 2021 1 to Mar 1, 2021 2
Animation : Jumperman Death | Animation | Wee Boon | 0 - Must Have | 0% | 4 | 2021-03-03 | 2021-03-04 | bar: Mar 1, 2021 3 to Mar 1, 2021 4
Animation : Enemy Death | Animation | Wee Boon | 0 - Must Have | 0% | 4 | 2021-03-05 | 2021-03-07 | bar: Mar 1, 2021 5 to Mar 1, 2021 7
2D Sprite : Jumperman | Art | Wee Boon | 0 - Must Have | 100% | 4 | 2021-01-18 | 2021-01-19 | bar: Jan 18, 2021 18 to Jan 18, 2021 19
2D Sprite : Slime | Art | Wee Boon | 0 - Must Have | 100% | 4 | 2021-01-19 | 2021-01-20 | bar: Jan 18, 2021 19 to Jan 18, 2021 20
2D Sprite : Bat | Art | Min Yi | 0 - Must Have | 100% | 4 | 2021-02-03 | 2021-02-04 | bar: Feb 1, 2021 3 to Feb 1, 2021 4
2D Sprite : Squirrel | Art | Min Yi | 0 - Must Have | 100% | 4 | 2021-02-03 | 2021-02-04 | bar: Feb 1, 2021 3 to Feb 1, 2021 4
Art : Grass Tile (Collapsible) | Art | Wee Boon | 0 - Must Have | 100% | 4 | 2021-01-23 | 2021-01-24 | bar: Jan 18, 2021 23 to Jan 18, 2021 24
Art : Special Tile (Interactible) | Art | Min Yi | 0 - Must Have | 100% | 2 | 2021-02-01 | 2021-02-02 | bar: Feb 1, 2021 1 to Feb 1, 2021 2
Art : Gravel Tile | Art | Dallas | 0 - Must Have | 100% | 2 | 2021-02-01 | 2021-02-02 | bar: Feb 1, 2021 1 to Feb 1, 2021 2
Art : Goal Tile | Art | Dallas | 0 - Must Have | 100% | 2 | 2021-01-25 | 2021-01-26 | bar: Jan 25, 2021 25 to Jan 25, 2021 26
Levels
Tiles : Collapsible | Level | Bryan | 0 - Must Have | 100% | 1 | 2021-02-01 | 2021-02-03 | bar: Feb 1, 2021 1 to Feb 1, 2021 3
Tiles : Non-Collapsible | Level | Bryan | 0 - Must Have | 100% | 1 | 2021-02-01 | 2021-02-03 | bar: Feb 1, 2021 1 to Feb 1, 2021 3
Tiles : Special | Level | Bryan | 0 - Must Have | 100% | 1 | 2021-02-08 | 2021-02-10 | bar: Feb 8, 2021 8 to Feb 8, 2021 10
Tiles : Goal | Level | Bryan | 0 - Must Have | 100% | 1 | 2021-02-04 | 2021-02-07 | bar: Feb 1, 2021 4 to Feb 1, 2021 7
Art : Grass Tile (Collapsible) | Level | Wee Boon | 0 - Must Have | 100% | 4 | 2021-01-25 | 2021-01-27 | bar: Jan 25, 2021 25 to Jan 25, 2021 27
Art : Special Tile (Interactible) | Level | Min Yi | 0 - Must Have | 100% | 2 | 2021-02-01 | 2021-02-03 | bar: Feb 1, 2021 1 to Feb 1, 2021 3
Art : Gravel Tile | Level | Dallas | 0 - Must Have | 100% | 2 | 2021-02-04 | 2021-02-07 | bar: Feb 1, 2021 4 to Feb 1, 2021 7
Art : Goal Tile | Level | Dallas | 0 - Must Have | 100% | 2 | 2021-01-28 | 2021-01-31 | bar: Jan 25, 2021 28 to Jan 25, 2021 31
Tutorial Level | Level | Wee Boon | 0 - Must Have | 50% | 6 | 2021-02-22 | 2021-02-23 | bar: Feb 22, 2021 22 to Feb 22, 2021 23
Level 1 | Level | Wee Boon | 0 - Must Have | 0% | 6 | 2021-02-24 | 2021-02-28 | bar: Feb 22, 2021 24 to Feb 22, 2021 28
Level 2 | Level | Min Yi | 1 - Should Have | 0% | 6 | 2021-03-01 | 2021-03-04 | bar: Mar 1, 2021 1 to Mar 1, 2021 4
Level 3 | Level | Min Yi | 1 - Should Have | 0% | 6 | 2021-03-04 | 2021-03-07 | bar: Mar 1, 2021 4 to Mar 1, 2021 7
Level 4 | Level | Min Yi | 2 - Could Have | 0% | 6 | 2021-03-07 | 2021-03-10 | bar: Mar 8, 2021 8 to Mar 8, 2021 11
Level 5 | Level | Min Yi | 2 - Could Have | 0% | 6 | 2021-03-10 | 2021-03-13 | bar: Mar 8, 2021 11 to Mar 8, 2021 14
Level 6 | Level | Min Yi | 2 - Could Have | 0% | 6 | 2021-03-13 | 2021-03-16
Level 7 | Level | Min Yi | 2 - Could Have | 0% | 6 | 2021-03-16 | 2021-03-19 | bar: Mar 15, 2021 15 to Mar 15, 2021 18
Level 8 | Level | Min Yi | 2 - Could Have | 0% | 6 | 2021-03-19 | 2021-03-22 | bar: Mar 15, 2021 18 to Mar 15, 2021 21
Level 9 | Level | Min Yi | 2 - Could Have | 0% | 6 | 2021-03-22 | 2021-03-25 | bar: Mar 22, 2021 22 to Mar 22, 2021 25
Level 10 | Level | Min Yi | 2 - Could Have | 0% | 6 | 2021-03-25 | 2021-03-28 | bar: Mar 22, 2021 25 to Mar 22, 2021 28
Systems
Tile collapsing system | Systems | Bryan | 0 - Must Have | 100% | 6 | 2021-01-22 | 2021-01-24 | bar: Jan 18, 2021 22 to Jan 18, 2021 24
Graphics: Font | Systems | Bryan | 0 - Must Have | 100% | 2 | 2021-01-30 | 31/2/2021 | bar: Jan 25, 2021 30 to Jan 25, 2021 31
Helper functions: Texture rendering with Alpha Engine | Systems | Bryan | 0 - Must Have | 30% | 8 | 2021-01-18 | 2021-01-24 | bar: Jan 18, 2021 18 to Jan 18, 2021 24
Collision detection: player and goal tile | Systems | Bryan | 0 - Must Have | 100% | 1 | 2021-01-25 | 2021-01-26 | bar: Jan 25, 2021 25 to Jan 25, 2021 26
Collision detection: enemy and player | Systems | Bryan | 0 - Must Have | 20% | 6 | 2021-02-08 | 2021-02-14 | bar: Feb 8, 2021 8 to Feb 8, 2021 14
Leaderboard system | Systems | Bryan | 1 - Should Have | 0% | 6 | 2021-03-08 | 2021-03-14 | bar: Mar 8, 2021 8 to Mar 8, 2021 14
Pause feature | Systems | Bryan | 1 - Should Have | 100% | 2 | 2021-01-27 | 2021-01-29 | bar: Jan 25, 2021 27 to Jan 25, 2021 29
Tile shake before collapsing | Systems | Bryan | 2 - Could Have | 0% | 6 | 2021-02-15 | 2021-02-18 | bar: Feb 15, 2021 15 to Feb 15, 2021 18
Autosave System | Systems | Bryan | 1 - Should Have | 0% | 6 | 2021-02-22 | 2021-02-28 | bar: Feb 22, 2021 22 to Feb 22, 2021 28
Sounds
Audio Integration using FMod | Sounds | Bryan | 0 - Must Have | 0% | 10 | 2021-03-15 | 2021-03-21 | bar: Mar 15, 2021 15 to Mar 15, 2021 21
Enemy Death Sound | Sounds | Dallas | 0 - Must Have | 0% | 2 | 2021-03-15 | 2021-03-15 | bar: Mar 15, 2021 15
Jumperman Death Sound | Sounds | Dallas | 0 - Must Have | 0% | 2 | 2021-03-17 | 2021-03-17 | bar: Mar 15, 2021 17
Jump Sound | Sounds | Dallas | 0 - Must Have | 0% | 2 | 2021-03-19 | 2021-03-19 | bar: Mar 15, 2021 19
Tile Collapse Sound | Sounds | Dallas | 2 - Could Have | 0% | 2 | 2021-03-21 | 2021-03-21 | bar: Mar 15, 2021 21
User Interface
Main Menu | UI | Dallas | 0 - Must Have | 30% | 4 | 2021-02-15 | 2021-02-21 | bar: Feb 15, 2021 15 to Feb 15, 2021 21
HUD | UI | Bryan | 0 - Must Have | 50% | 2 | 2021-02-13 | 2021-02-14 | bar: Feb 8, 2021 13 to Feb 8, 2021 14
Pause Menu | UI | Dallas | 0 - Must Have | 50% | 4 | 2021-03-08 | 2021-03-11 | bar: Mar 8, 2021 8 to Mar 8, 2021 12
Buttons | UI | Bryan | 1 - Should Have | 0% | 8 | 2021-02-22 | 2021-02-27 | bar: Feb 22, 2021 22 to Feb 22, 2021 27
Visuals : FONT + Art style definition | UI | Wee Boon | 0 - Must Have | 80% | 4 | 2021-02-15 | 2021-02-21 | bar: Feb 15, 2021 15 to Feb 15, 2021 21
Visuals : Main Menu | UI | Dallas | 0 - Must Have | 50% | 4 | 2021-02-22 | 2021-02-23 | bar: Feb 22, 2021 22 to Feb 22, 2021 23
Visuals : HUD | UI | Dallas | 0 - Must Have | 50% | 4 | 2021-02-24 | 2021-02-25 | bar: Feb 22, 2021 24 to Feb 22, 2021 25
Visuals : Pause Menu | UI | Dallas | 0 - Must Have | 50% | 4 | 2021-02-26 | 2021-02-27 | bar: Feb 22, 2021 26 to Feb 22, 2021 27
Visuals : Death Screen | UI | Dallas | 0 - Must Have | 50% | 4 | 2021-03-01 | 2021-03-04 | bar: Mar 1, 2021 1 to Mar 1, 2021 4
Menu : Level Selection | UI | Dallas | 0 - Must Have | 0% | 6 | 2021-03-08 | 2021-03-11 | bar: Mar 8, 2021 8 to Mar 8, 2021 11
Visuals : Level Selection | UI | Dallas | 0 - Must Have | 0% | 4 | 2021-03-15 | 2021-03-18 | bar: Mar 15, 2021 15 to Mar 15, 2021 18